## Time sheet
| December |  | January | February | March |  | April | May
Padagogical Guidelines
Green capsules (1) |  |  |  | Short Green info capsule | Short Green info capsule |  | Short Green info capsule | Short Green info capsule
Ped day (January 14) (2) | Prepare content for green teaching practices w/ PACTE2D
Printing issues (3) | Better printing practices (plan) |  |  |  |  | Monitor progress
Alternative Transportation
Surveys (September - STS) | Gather and analyse data from surveys
Surveys (transportation habits) | Elaborate questions for upcoming survey
Velo libre-service (pilot project) |  |  | Find partners to help repair bikes | Have bikes refurbished |  | Organize and host a bike clinic (repais, settings,…) | Pilot project (velo libre-service) |  | Reflection
Communications
Internet site ergonomy (4) |  | Develop content and promote site
Partner bank (5) |  |  | Gather partners in the community that can provide material for pedagogical content (descriptive organisational "business cards") |  |  |  |  | Launch website (Union meeting)
Waste Management
Organizing a composting / recycling event (6) | Find partners to help students gather information on recycling and composting |  |  | Have students develop an event over issues of waste disposal/management | Event in lobby
(#): See Notes
In progress:
-One capsule about on-screen grading in prep.
-Will be available during reading week.
Done:
-10+ particpants.
-Main concern: use of paper.
-Will repeat. Focus on sustainability as a ped tool (see website).
-Both surveys are completed.
-STS survey is processed.
-Survey on sustainability will be distributed shortly.
-Automatic PDF.
-Students to be charged for printing.
-Econotone and front/back not a priority.
In progress:
-Discussions w/ CSA and La Déraille.
-After verifications (UdeS and CdeS) insurrance coverage not affected.
In progress:
-Comments, material and forum participation
-Link from home page
www.greenchamplain.weebly.com
-Stikers done by Judith and posted on water fountains
-Earth Day (Apr22: waste management and transportation).
-Need ideas for hand-outs and activities.
-Sebastien Nanetl's students to provide w/ posters and ideas for on-line mktg.
-Facebook page.
-Stickers for recyc. bins (dos and don'ts)

## Notes
(1) | Short information capsules vehiculed through website and email (community) with examples of environmentally-friendly actions in day-to-day teaching practices.
(2) | Pacte2D specializes in issues over sustainable development in pedagogy. They offered to present a workshop during Ped Day. Their presentation would be combined with discussions, exchanges on possible improvements of our own practices.
(3) | P. Roy and J. Lacombe found ways to reduce printing and printing costs. Suggestions include automatic back-to-back printing in labs, use of econotone in labs, automatic pdf printing. These should be in place in the coming weeks.
(4) | Students from S. Nantel's Marketing course are currently working on suggestions on the website's content and esp. use of complementary social media.
(5) | Reaching out to local organizations that would like to provide professors w/ material they could use for class content (ex: year-end reports, challenges with recruitment, promotion and other resources).
(6) | The purpose of this event is raise awareness over the proper way to use recycling bins (reminder) and promote composting. Students are thought of for the hosting of this ideally week-long event. Activities could be suggested (i.e. composting in the lounges, how to plan green events, ...).